## CRM- REGISTRATION FORM
WBS NUMBER | TASK TITLE | PCT OF TASK COMPLETE | 2021-01-01 | [19 empty] | 2021-02-02
|  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
|  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | APPLICATION FORM-FULL TIME TEACHERS | bar: WEEK 1 M to WEEK 3 F
1.1 | Save Full-time teachers data | 100% | bar: WEEK 1 M to WEEK 1 T
1.1.1 | Show teachers data for admin (PR department) | 100% | bar: WEEK 1 W to WEEK 2 F
1.2 | Edit form for teacher | 100%
1.3 | View and print form's full-time teacher | 100%
1.4 | Export Excel from data list | 100%
1.5 | Validate form | 100% | bar: WEEK 2 M to WEEK 3 M
1.6 | Send mail when save successfull | 100% | bar: WEEK 3 T
1.7 | Mail setting | bar: WEEK 3 W
2 | APPLICATION FORM-POTENTIAL SEED TEACHERS | bar: WEEK 1 M to WEEK 3 F
3.1 | Create form page | 100% | bar: WEEK 1 M to WEEK 1 T
3.2 | Create popup add new form | 100% | bar: WEEK 1 W to WEEK 1 R
3.2.1 | Create popup edit form | 100% | bar: WEEK 1 F to WEEK 2 F
3.2.2 | Create admin page manage forms | 100%
3.3 | Create database | 100%
3.3.1 | Save form data | 100%
3.2.3 | Edit form data | 100%
4.3 | View and pritn form | 100% | bar: WEEK 3 R
3.3.2 | pagination and search | 100% | bar: WEEK 3 R
3.2.4 | Test | 100%
3 | DESCRIPTION OF NOTIFICATION SOFTWARE NEEDS FORM | bar: WEEK 1 M to WEEK 3 F
2.1 | Create form page | 0%
2.2 | Create popup add new form | 0%
2.3 | Create popup edit form | 0%
2.4 | Create admin page manage forms | 0%
2.5 | Create database | 0%
2.6 | Save form data | 0%
2.7 | Edit form data | 0%
2.8 | View and pritn form | 0%
2.9 | pagination and search | 0%
| Test | 0%

## CRM
WBS NUMBER | TASK TITLE | PCT OF TASK COMPLETE
|  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  | 2021-11-01 |  |  |  | 2021-12-01
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
MANAGE UNIFORM SUBSCRIPTION SET UP | bar: 2021-05-01 W1 to 2021-05-01 W4; 2021-08-01 W1 to 2021-10-01 W1; 2021-10-01 W4
1.1 | Get requirement | bar: 2021-05-01 W1
1.2 | Design database | bar: 2021-05-01 W1 to 2021-05-01 W2
1.3 | Design data flow | bar: 2021-05-01 W2
1.4 | Design user interface | bar: 2021-05-01 W3
1.5 | Create user interface | bar: 2021-05-01 W4
REGISTER TO BUY UNIFORMS | bar: 2021-05-01 W1 to 2021-05-01 W4; 2021-07-01 W1; 2021-08-01 W1 to 2021-10-01 W1; 2021-10-01 W4
2.1 | Create registration form | bar: 2021-06-01 W1
2.2 | Save data from Form | bar: 2021-06-01 W1
2.3 | Validate data form | bar: 2021-06-01 W2
2.4 | Edit/Update data form | bar: 2021-06-01 W2 to 2021-06-01 W3
2.5 | Send mail when student register successful | bar: 2021-06-01 W3
MANAGE UNIFORM SUBSCRIPTION LIST | bar: 2021-05-01 W1 to 2021-06-01 W1; 2021-07-01 W1; 2021-08-01 W1 to 2021-10-01 W1; 2021-10-01 W4
3.1 | Create data table | bar: 2021-06-01 W4
3.2 | Export excel | bar: 2021-06-01 W4
DEMO AND FIX BUG | bar: 2021-05-01 W1 to 2021-06-01 W1; 2021-07-01 W1; 2021-08-01 W1 to 2021-10-01 W1; 2021-10-01 W4
4.1 | First Demo | bar: 2021-07-01 W1
4.2 | Fix bug | bar: 2021-07-01 W1
LESSON PLAN ONLINE | bar: 2021-05-01 W1 to 2021-06-01 W1; 2021-07-01 W1; 2021-08-01 W1 to 2021-10-01 W1; 2021-10-01 W4
5.1 | Get requirement | bar: 2021-07-01 W2
5.2 | Design database | bar: 2021-07-01 W3
5.3 | Design data flow | bar: 2021-07-01 W3
5.4 | Design user interface | bar: 2021-07-01 W4
5.5 | Create user interface | bar: 2021-07-01 W4 to 2021-08-01 W1
5.6 | Create lesson plan form | bar: 2021-08-01 W2
5.7 | Create registration form | bar: 2021-08-01 W3
5.8 | Save data from Form | bar: 2021-08-01 W4
5.9 | Validate data form | bar: 2021-09-01 W1
6 | Edit/Update data form | bar: 2021-09-01 W2
6.1 | Send mail when teacher register successful | bar: 2021-09-01 W3
6.2 | Create data table | bar: 2021-09-01 W4
6.3 | Export excel | bar: 2021-10-01 W1
6.4 | Filter data | bar: 2021-10-01 W2
6.5 | First Demo | bar: 2021-10-01 W3
6.6 | Fix bug | bar: 2021-10-01 W3

## Website
WBS NUMBER | TASK TITLE | PCT OF TASK COMPLETE | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01
|  |  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
1 | DISPLAY AND AUTHENTICATION
1.1 | Login administrator | 100%
1.1.1 | Edit content | 100%
1.2 | Display notifications on home page | 100%
1.3 | Display events on home page | 100%
1.4 | Display news slideshow on home page | 100%
1.5 | Form on Contact page | 100%
1.6 | Form on Contact page | 100%
1.7 | Test | 100%
2 | MEDIA MANAGEMENT
2.1 | Create media management page | 100%
2.2 | Upload file | 100%
2.3 | Select file | 100%
2.4 | Display folder | 100%
2.5 | Display file | 100%
CALENDAR MANAGEMENT
3.1 | Create calendar management page | 100%
3.2 | Link Calendar Google | 100%
3.3 | Display calendar | 100%
3.4 | Create event | 100%
3.5 | Edit Event | 100%
MULTIPLE LANGUAGES
4.1 | Create English pages | 100%
4.2 | Create English category | 100%
4.3 | Create Content for English pages | 100%
4.4 | Fix anh Test | 100%
PERMISSION
4.1 | Create Role | 100%
4.2 | Edit Role | 100%
4.3 | Create permission | 100%

## Canvas management
WBS NUMBER | TASK TITLE | PCT OF TASK COMPLETE
|  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1.1 | Create new Accout | 100%
1.2 | Add student to Course | 100%
1.3 | Access Permissions | 100%
1.4 | Create new Course | 100%
1.5 | Add teacher to Course | 100%

## Email management
WBS NUMBER | TASK TITLE | PCT OF TASK COMPLETE
|  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1.1 | Create new Account | 100% | bar: 2021-05-01 W1
1.2 | Edit Account | 100% | bar: 2021-05-01 W2
1.3 | Add user to Group | 100% | bar: 2021-05-01 W3
1.4 | Access Permissions | 100% | bar: 2021-05-01 W4